## Register
ID | Audit | Finding | Severity | Fix class | Status | Verification | Verification note / evidence
SEC-C1 | Security | Live production credentials and employee PII committed to the repo, in the one path CI is told not to scan | Critical | Process + purge | Fixed | Verified in code | Scanner un-excluded AND pattern set widened; 7 credential files cleaned (5 more than the audit cited, incl. 2 Groq keys CI found). CREDENTIALS ROTATED BY OWNER 2026-08-04. History still contains them — purge declined, rotation makes it harmless.
SEC-C2 | Security | Logout does not end the session; the refresh token stays valid | Critical | Code, quick | Fixed | Verified in code | Access tokens now carry `sid`; logout revokes the session from the TOKEN, not a body field the client never sent. Both issuance paths (login + refresh rotation) carry it — a test asserts every signAccessToken call site does. Response reports session_revoked honestly. Verified to FAIL 4/6 against the old service. Commit 809caad.
SEC-C3 | Security | No brute-force protection on any authentication endpoint; failed-login counter never enforced | Critical | Code, quick | Fixed | Verified in code | Limiters on all 11 credential surfaces across 3 tiers, AND the failed-login counter is now enforced as a decaying cooldown (migration 0495). 7 assertions on the curve.
SEC-H1 | Security | The AI assistant executes business writes with no permission check at all | High | Code | Open | As reported
SEC-H2 | Security | Platform Console credential-store routes have no capability gate | High | Code, quick | Fixed | Verified in code | requireCap on all 8 routes; settings.read/write + migration 0032; structural test asserts all 47 platform routes are gated.
SEC-H3 | Security | Request-body keys become SQL column identifiers on modules using the passthrough validator | High | Code | Open | As reported
SEC-H4 | Security | MOD-67 'edit' can take over any account, including the CEO, with no re-authentication | High | Code | Open | As reported
SEC-H5 | Security | Rate limiting is bypassable: trust proxy true with an IP-keyed in-memory store | High | Config + code | Fixed | Verified in code | Redis-backed limiter store; trust proxy is now a hop count (TRUST_PROXY_HOPS), not `true`.
SEC-H6 | Security | Portal and platform accounts protected by an 8-char password, no complexity or breach check | High | Code, quick | Open | As reported
SEC-M1 | Security | Access tokens are not session-bound: revocation does not revoke | Medium | Code | Open | As reported
SEC-M2 | Security | killSession has no ownership predicate | Medium | Code, quick | Fixed | Verified in code | killSession is now always scoped to the acting user. Folded into the SEC-C2 fix. Commit 809caad.
SEC-M3 | Security | Document vault authorization is module-level, not record-level | Medium | Code | Open | As reported
SEC-M4 | Security | The Socket.IO handshake lets the client name its own tenant | Medium | Code | Open | As reported
SEC-M5 | Security | One JWT secret across all three auth tiers, and no tenant claim in any token | Medium | Structural | Open | As reported
SEC-M6 | Security | Platform tier has no session store, no revocation and no 2FA | Medium | Structural | Open | As reported
SEC-M7 | Security | One database credential and one encryption key shared across all tenants | Medium | Structural | Open | As reported
SEC-M8 | Security | CSP permits unsafe-inline scripts application-wide | Medium | Config | Open | Verified in code | server.js: script-src ['self','unsafe-inline'], script-src-attr ['unsafe-inline']
SEC-M9 | Security | Dependency vulnerabilities present, gate non-blocking, no SAST or Dependabot | Medium | CI | Open | Verified in code | ci.yaml:79 continue-on-error: true on npm audit
SEC-L1 | Security | Containers run as root; compose bind-mounts the document vault into them | Low | Config, quick | Open | As reported
SEC-L2 | Security | Redis unauthenticated and keyspace not tenant-namespaced; invalidateGrants uses blocking KEYS | Low | Config + code | Open | As reported
SEC-L3 | Security | Refresh token in web storage | Low | Code (blocked by M8, C2) | Open | As reported
SEC-L4 | Security | Logger redaction misses refresh_token, access_token, password_hash, totp_secret_enc, secret_enc | Low | Config, quick | Fixed | Verified in code | REDACT_PATHS widened; both top-level and nested forms generated from SENSITIVE_KEYS.
SEC-L5 | Security | The anonymous-surface test is shallow - matches authMiddleware anywhere in the router | Low | Test, quick | Open | As reported
SEC-L6 | Security | src/middleware/audit.js is dead code, never imported or mounted | Low | Delete | Open | As reported
DI-5.5 | Data Integrity | Asset depreciation never posts to the GL and records itself as posted | Critical | Code, quick | Fixed | Verified in code | Depreciation now reaches the GL: account_code + sourceDocRef, and a ledger rejection FAILS the call instead of setting posted=true with entry_id NULL. 11 assertions, verified to FAIL against the pre-fix file. Sweep found only asset+payroll; a grep-as-a-test blocks a third. Commit 62a9646. NOTE: existing bad rows need scripts/db/reconcile-depreciation.js.
DI-5.1 | Data Integrity | Inventory balance: no transaction, no lock, no DB floor | Critical | Code + constraint | Open | As reported
DI-5.2 | Data Integrity | Shared CRUD kit writes business row, event and audit as three separate commits | Critical | Code, mechanical | Open | As reported
DI-1.1 | Data Integrity | ~100 money/quantity columns with no CHECK constraint | Critical | Migration + data probe | Open | As reported
DI-1.2 | Data Integrity | No cross-row sum invariants (over-allocation, over-justification) | Critical | Migration + data probe | Open | As reported
DI-2.1 | Data Integrity | ON DELETE CASCADE on financial and inventory history | Critical | Migration, careful | Open | As reported
DI-1.3 | Data Integrity | Multi-currency ledger lines are stored but never reconciled to a base currency | High | Migration + code | Open | As reported
DI-1.6 | Data Integrity | doc_number is not unique anywhere | High | Migration + dedupe | Open | As reported
DI-1.8 | Data Integrity | tax_code effective windows can overlap, producing wrong VAT silently | High | Migration + code | Open | As reported
DI-1.9 | Data Integrity | cached_receivables read but never written; credit limit inert | High | Code, quick | Open | As reported
DI-2.2 | Data Integrity | 295 of 351 foreign keys have no index on the referencing column | High | Migration, online | Open | As reported
DI-2.4 | Data Integrity | Sandbox actor-FK guard applied inconsistently | High | Code + design | Open | As reported
DI-3.1 | Data Integrity | Migration application is not atomic with its ledger entry | High | Tooling | Open | As reported
DI-3.2 | Data Integrity | A partial fleet upgrade leaves tenants on different schema versions | High | Tooling | Open | As reported
DI-3.3 | Data Integrity | Migration files and the live schema have already drifted (notification_preference) | High | Verify + tooling | Open | As reported
DI-3.5 | Data Integrity | No migration is reversible; no down concept exists in the tooling | High | Policy | Partially fixed | As reported | New migrations must declare -- DOWN or -- IRREVERSIBLE (CI gate). The 92 pre-existing migrations are still irreversible and deliberately not retro-fitted.
DI-5.3 | Data Integrity | Receipt allocation reads unlocked and can over-allocate | High | Code + constraint | Open | As reported
DI-5.4 | Data Integrity | Tax-code supersession splits across two transactions | High | Code, quick | Open | As reported
DI-6.2 | Data Integrity | Audit tamper-evidence chain declared but before_hash/after_hash never populated | High | Code, quick | Open | As reported
DI-6.3 | Data Integrity | Financial and inventory mutations audited inconsistently; depends on service discipline | High | Code + triggers | Open | As reported
DI-6.4 | Data Integrity | stock_movement is mutable, cascade-deleted, and can be incomplete - no audit trail | High | Migration | Open | As reported
DI-7.1 | Data Integrity | Missing uniqueness on document numbers and payment allocations | High | Migration + dedupe | Open | As reported
DI-1.4 | Data Integrity | currency typing inconsistent - 8 columns FK to currency(code), 9 identical ones do not | Medium | Migration | Open | As reported
DI-1.5 | Data Integrity | chart_of_accounts and other self-referencing hierarchies have no cycle guard | Medium | Migration | Open | As reported
DI-2.3 | Data Integrity | No ON UPDATE clause on any foreign key | Medium | Decision | Open | As reported
DI-3.4 | Data Integrity | Duplicate migration numbers - correctly diagnosed and correctly left alone | Medium | Prevention only | Open | As reported
DI-3.6 | Data Integrity | EXCEPTION WHEN OTHERS THEN NULL in data-seeding migrations 0467/0468 | Medium | Forward-fix | Open | As reported
DI-4.1 | Data Integrity | The RLS apparatus references a migration that does not exist | Medium | Remove or implement | Open | As reported
DI-4.2 | Data Integrity | 32 references to a non-existent shared.* schema | Medium | Remove | Open | As reported
DI-5.6 | Data Integrity | Tenant provisioning and sandbox wipe are not transactional | Medium | Code | Open | As reported
DI-6.5 | Data Integrity | Silent overwrite of financial figures; locked documents protected only in the service layer | Medium | Migration | Open | As reported
DI-7.2 | Data Integrity | Missing indexes on columns that gate correctness-critical queries | Medium | Migration, online | Open | As reported
DI-1.7 | Data Integrity | The section 23.14 dictionary invariant is one-directional | Low | Migration | Open | As reported
OBS-A2 | Observability | The health check is structurally incapable of failing - and it is the deploy gate | Critical | Quick win | Fixed | Verified in code | /api/health/ready probes Postgres+Redis, 503s honestly. Verified with the DB down.
OBS-A1 | Observability | There is no alerting. At all. | Critical | Quick win | Fixed | Verified in code | Repo side wired + loud boot warning. MONITOR AND WEBHOOK CONFIGURED BY OWNER 2026-08-04.
OBS-A3 | Observability | Redis outage boots the app silently degraded | Critical | Quick win | Open | As reported
OBS-A6 | Observability | Dead-lettered business events are a silent black hole | Critical | Medium | Open | As reported
OBS-E1 | Observability | No centralised error tracking of any kind | Critical | Medium | Fixed | Verified in code | shared/observability/error-reporter.js — every 5xx, uncaughtException and unhandledRejection reports with tenant/user/request_id/route/build. Dedupe + id normalisation + frame-drift stability + 20/min ceiling so the channel stays usable. 4xx and ZodError never reported. Commit e78a566.
OBS-E2 | Observability | Frontend errors are completely invisible | Critical | Quick win | Fixed | Verified in code | POST /api/client-errors + client/src/lib/error-reporting.ts covering render, window 'error' and unhandledrejection. ErrorBoundary's dead onError hook now reports by default. sendBeacon survives the post-crash reload. Commit e78a566.
OBS-L1 | Observability | No HTTP access log exists at all - pino-http is a dependency, mounted nowhere | Critical | Quick win | Fixed | Verified in code | pino-http mounted.
OBS-L2 | Observability | The money path is entirely log-silent - zero logger calls in finance or accounting | Critical | Medium | Open | As reported
OBS-L3 | Observability | Almost no log line carries tenant or user, though AsyncLocalStorage already holds both | Critical | Quick win | Fixed | Verified in code | pino mixin injects tenant+user into ALL ~120 call sites with zero edits; auth.js back-fills the user the context captured as null.
OBS-M1 | Observability | No metrics of any kind, no dashboard, no baseline | Critical | Medium | Open | As reported
OBS-T1 | Observability | Reconstructing one failed request is effectively impossible | Critical | Phases 2+4 | Open | As reported
OBS-I1 | Observability | No runbook, no on-call, no incident process | Critical | Process | Open | As reported
OBS-I2 | Observability | No rollback procedure and no artifact to roll back to | Critical | Medium | Fixed | Verified in code | Images tagged by commit and retained; scripts/rollback.sh added.
OBS-A4 | Observability | No restart: policy on any service | High | Quick win | Fixed | Verified in code | restart: unless-stopped on all five services; migrate stays 'no'.
OBS-A5 | Observability | The worker is entirely unmonitored | High | Quick win | Open | As reported
OBS-E3 | Observability | The correlation ID is minted, then thrown away; persisted nowhere | High | Quick / Medium | Open | As reported
OBS-E4 | Observability | uncaughtException keeps a poisoned process alive | High | Quick win | Fixed | Verified in code | Process now exits on uncaughtException; paired with OBS-A4.
OBS-L4 | Observability | Sensitive data leaking into logs, including row values via pg err.detail | High | Quick win | Fixed | Verified in code | Same fix as SEC-L4, incl. pg err.detail. Landed BEFORE any log shipping.
OBS-L7 | Observability | Logs are neither durable nor shipped; lost on every deploy | High | Quick / Medium | Open | As reported
OBS-M2 | Observability | Business metrics unobservable though the data already exists | High | Medium | Open | As reported
OBS-T2 | Observability | No timing recorded anywhere | High | Quick win | Fixed | Verified in code | Response time on every access-log line.
OBS-T4 | Observability | Auth, RBAC and tenant middleware log nothing | High | Quick win | Open | As reported
OBS-I3 | Observability | Migrations have no rollback path and run before the app rolls; no automated backup | High | Medium | Open | As reported
OBS-I4 | Observability | The deploy has no real smoke test and no auto-rollback | High | Quick win | Partially fixed | As reported | Smoke test can now fail and the deploy exits non-zero. Auto-rollback NOT wired — rollback.sh has never been executed, and automating an unproven recovery path is worse than manual.
OBS-I6 | Observability | Single-host topology with no capacity signal | High | Deeper | Open | As reported
OBS-A7 | Observability | Failed BullMQ jobs accumulate unwatched | Medium | Medium | Open | As reported
OBS-L5 | Observability | Level discipline inverted - real failures logged at warn, stacks discarded | Medium | Quick win | Open | As reported
OBS-L6 | Observability | The runbook documents a log location that does not exist | Medium | Quick win | Open | As reported
OBS-M3 | Observability | Slow queries warn but are never measured | Medium | Quick win | Open | As reported
OBS-T3 | Observability | No cross-process correlation into workers | Medium | Medium | Open | As reported
OBS-I5 | Observability | Deploys are unattributed and unannounced | Medium | Quick win | Fixed | Verified in code | Build identity + deploy announcements to ALERT_WEBHOOK_URL on start/success/failure.
API-F1 | API Contract | Eighteen deliberate client errors are returned to consumers as 500 INTERNAL_ERROR | Critical | Code (BC) | Fixed | Verified in code | error-handler honours err.status for 4xx; thrown 5xx still flattens to a generic 500. Fixed BEFORE alerting went live.
API-F6 | API Contract | Two unrelated resources share the base path /inbound | Critical | Code (BC) | Fixed | Verified in code | sales/inbound_intake moved to /intake; 4 client callers updated; waiver list now empty and the boot guard is unconditional. BREAKING.
API-F18 | API Contract | There is no versioning of any kind - no prefix, header, sunset or deprecation mechanism | Critical | Structural | Open | As reported
API-F20 | API Contract | Platform secret management has no capability check (8 routes) | Critical | Code, quick | Fixed | Verified in code | Same fix as SEC-H2.
API-F30 | API Contract | There is no mechanism that would catch a contract regression | Critical | CI + test | Open | As reported
API-F2 | API Contract | Three different response shapes for 'your input was invalid' | High | Code (BC) | Open | As reported
API-F15 | API Contract | 60 write routes accept an unvalidated body (17% of writes) | High | Code | Open | As reported
API-F16 | API Contract | Query and path parameters are almost never validated | High | Code | Open | As reported
API-F19 | API Contract | Modules can vanish from the API without any error | High | Additive | Fixed | Verified in code | Skipped modules recorded, logged at error, and surfaced on /api/health/ready.
API-F21 | API Contract | Structurally identical lifecycle endpoints require different permissions | High | Code (BC) | Open | As reported
API-F25 | API Contract | No API spec exists; the one artefact that does is 19% complete and has drifted | High | Docs | Open | As reported
API-F26 | API Contract | No list endpoint reports a total, so no consumer can paginate | High | Additive | Partially fixed | Verified in code | TOTAL_COL/splitTotal added in query-helpers.js and wired into 4 finance repos (final_invoice, journal_entry, proforma, smart_receivables) via commit 9c5337d, surfaced as X-Total-Count. 198 of 202 collection GETs still return a bare array
API-F27 | API Contract | 17 list endpoints have no LIMIT at all, including /sessions and /permissions | High | Code (BC) | Open | As reported
API-F3 | API Contract | Middleware-level errors omit request_id | Medium | Code | Open | As reported
API-F4 | API Contract | A platform-host request to the tenant API returns 500 | Medium | Code | Open | As reported
API-F7 | API Contract | /portal and /portals are different products | Medium | Code (BC) | Open | As reported
API-F8 | API Contract | Resource-name pluralisation is ~63/37 | Medium | Code (BC) | Open | As reported
API-F9 | API Contract | Module-to-URL mapping is not derivable, and three modules claim the tenant root | Medium | Code (BC) | Open | As reported
API-F10 | API Contract | Grouping depth is arbitrary | Medium | Code (BC) | Open | As reported
API-F11 | API Contract | Two idioms for the same operation: lifecycle transitions | Medium | Code (BC) | Open | As reported
API-F12 | API Contract | DELETE means two different things (hard delete vs soft archive) | Medium | Code (BC) | Open | As reported
API-F17 | API Contract | PATCH bodies are create.partial(), so every writable field is patchable | Medium | Code | Open | As reported
API-F22 | API Contract | In Smart Comms, 'view' authorises writes | Medium | Code (BC) | Open | As reported
API-F23 | API Contract | Authenticated-but-ungated endpoints are correct, but undeclared | Medium | Docs | Open | As reported
API-F28 | API Contract | Filtering is undeclared, per-repo, and silently ignores typos | Medium | Docs + code (BC) | Open | As reported
API-F29 | API Contract | Sorting is not exposed anywhere | Medium | Additive | Open | As reported
API-F5 | API Contract | 188 error codes, no registry | Low | Docs | Open | As reported
API-F13 | API Contract | Identity in the body instead of the URL, and inverted nesting | Low | Code (BC) | Open | As reported
API-F14 | API Contract | Reads that are POSTs, and one read that writes | Low | Code (BC) | Open | As reported
API-F24 | API Contract | Unauthenticated routes - reviewed, all justified | Low | No action (positive finding) | Closed | As reported
PERF-S1 | Perf & Architecture | Tenant connection model caps the product at ~12 active tenants per API process | Critical | Structural | Open | Verified in code | registry.service.js:78 one pg.Pool per tenant, max = TENANT_POOL_MAX (env.js:66 default 8); unbounded Map, no eviction, no PgBouncer
PERF-S2 | Perf & Architecture | Three pool checkouts and three SET search_path round-trips per request | Critical | Structural | Open | As reported
PERF-S3 | Perf & Architecture | 123 of 126 tables sort by an unindexed created_at - 462x speedup available | Critical | Quick win | Fixed | Verified in code | Migration 0496 adds a created_at index to all 127 tenant tables that declare one (DDL-parsed: zero were indexed). Measured 462x. Plain CREATE INDEX because the migrator's multi-statement query is an implicit transaction block, where CONCURRENTLY cannot run. Targets verified against the DDL — but NOT YET EXECUTED. Commit 537a4af.
PERF-S4 | Perf & Architecture | Per-request recursive CTE over an unindexed tree (scope.parent_scope_id) | High | Quick + structural | Open | As reported
PERF-S5 | Perf & Architecture | Notification fan-out is an N+1 inside the business transaction | High | Structural | Open | As reported
PERF-S6 | Perf & Architecture | Every write pays 4-6 extra sequential round-trips | High | Quick win | Open | As reported
PERF-S7 | Perf & Architecture | No HTTP compression anywhere in the stack | High | Quick win | Open | As reported
PERF-S8 | Perf & Architecture | The entire frontend loads on first paint; code splitting is cosmetic | High | Quick win | Open | As reported
PERF-S9 | Perf & Architecture | invalidateGrants() blocks Redis and flushes every tenant | High | Quick win | Open | As reported
PERF-S10 | Perf & Architecture | hostCache is unbounded and keyed by attacker-controlled input | High | Quick win | Open | As reported
PERF-S11 | Perf & Architecture | 13 BullMQ workers share a single Redis connection | High | Structural | Open | As reported
PERF-S12 | Perf & Architecture | Socket.IO has no Redis adapter - realtime is single-process only | High | Structural | Open | As reported
PERF-S13 | Perf & Architecture | A full Chromium process is spawned per PDF | Medium | Structural | Open | As reported
PERF-S14 | Perf & Architecture | Context providers defeat memoization app-wide | Medium | Quick win | Open | As reported
PERF-S15 | Perf & Architecture | No client-side request cache; unconditional refetch and background polling | Medium | Quick win | Open | As reported
PERF-S16 | Perf & Architecture | Leading-wildcard ILIKE search guarantees a full scan | Medium | Quick win | Open | As reported
PERF-S17 | Perf & Architecture | OFFSET pagination degrades and spills to disk | Medium | Structural (BC) | Open | As reported
PERF-S18 | Perf & Architecture | No global rate limiting - noisy-neighbour risk across tenants | Medium | Quick win | Open | As reported
PERF-S19 | Perf & Architecture | 50 repos hand-roll an SQL builder that already exists | Low | Quick win | Open | As reported
PERF-S20 | Perf & Architecture | SQL identifiers are interpolated from object keys with no enforcement | Low | Structural | Open | As reported
TC-C1 | Test & CI/CD | Multi-tenant isolation (registry.service.js) - 0 of 10 functions covered | Critical | Deeper | Open | As reported
TC-C2 | Test & CI/CD | authMiddleware() uncovered; the patched token-replay fix has no regression test | Critical | Quick | Open | As reported
TC-C3 | Test & CI/CD | rbacCheck() and ceoCheck() uncovered - enforcement paths never run in a test | Critical | Quick | Open | As reported
TC-C4 | Test & CI/CD | identity-cache.js - 0 of 31 functions; grants, scope closure, invalidation | Critical | Deeper | Open | As reported
TC-D1 | Test & CI/CD | No rollback; docker image prune -f destroys the previous build | Critical | Deeper | Fixed | Verified in code | docker image prune no longer destroys the previous build; KEEP_IMAGES deep.
TC-D2 | Test & CI/CD | Migrations run pre-roll, no backup, zero down-migrations | Critical | Quick / process | Fixed | Verified in code | pg_dump before migrations, fatal if it fails; reversibility convention + CI gate for new migrations.
TC-CI1 | Test & CI/CD | main is unprotected; 45% direct pushes; each green push auto-deploys | Critical | Quick / process | Open | As reported
TC-C5 | Test & CI/CD | Money services 0% function coverage; only the rules layer is tested | High | Deeper | Open | As reported
TC-C6 | Test & CI/CD | All 4 integration suites permanently skipped - 11 tests dark in CI | High | Deeper | Open | As reported
TC-C7 | Test & CI/CD | WMS/inventory 7.3% functions - no unit or integration coverage | High | Deeper | Open | As reported
TC-C8 | Test & CI/CD | Orchestration outbox 0% - at-least-once idempotency unverified | High | Deeper | Open | As reported
TC-C9 | Test & CI/CD | Platform / tenant-provisioning surface 0% | High | Deeper | Open | As reported
TC-C10 | Test & CI/CD | Portal auth (external, customer-facing) 3.2% functions | High | Quick / deeper | Open | As reported
TC-C12 | Test & CI/CD | No API-level or E2E test; the middleware chain never runs as a chain | High | Deeper | Open | As reported
TC-Q2 | Test & CI/CD | refresh() untested; only its extracted predicate is | High | Quick | Open | As reported
TC-Q4 | Test & CI/CD | The money-path test mocks away determination and GL posting | High | Deeper | Open | As reported
TC-CI6 | Test & CI/CD | Migrations are never executed in CI; the first run is production | High | Deeper | Open | As reported
TC-CI7 | Test & CI/CD | The built image is never started; boot failures reach deploy | High | Quick | Open | As reported
TC-CI8 | Test & CI/CD | npm install not npm ci - CI does not test the dependency tree that gets deployed | High | Deeper | Open | As reported
TC-D3 | Test & CI/CD | migrateAllTenants has no containment; mixed-fleet state on failure | High | Deeper | Open | As reported
TC-D4 | Test & CI/CD | /api/health is shallow; the deploy gate cannot see a dead database | High | Quick | Fixed | Verified in code | Deploy gate now targets readiness, not liveness.
TC-D5 | Test & CI/CD | CI holds a long-lived (likely root) SSH session on production | High | Quick / deeper | Open | As reported
TC-D6 | Test & CI/CD | No pre-production environment for builds (deliberate; the PRD contradicts it) | High | Process | Open | As reported
TC-E1 | Test & CI/CD | Production .env is hand-maintained and validated only at boot, post-migration | High | Quick | Open | As reported
TC-R2 | Test & CI/CD | A running build cannot identify itself | High | Quick | Fixed | Verified in code | BUILD_SHA/BUILD_TIME baked into the image, surfaced on both health endpoints.
TC-CI2 | Test & CI/CD | main is red on 15% of runs; no always-deployable branch | High | Quick | Open | As reported
TC-C11 | Test & CI/CD | Frontend suite is presentational only; money, permissions and Live/Test untested; platform-console at zero | Medium | Deeper | Partially addressed | Verified in code | Client test files have grown from 3 to 15 since the audit; platform-console still at zero
TC-Q1 | Test & CI/CD | Coverage inflation - line coverage inflated by import-time execution | Medium | Quick | Open | As reported
TC-Q3 | Test & CI/CD | Hand-rolled regex SQL fakes silently absorb query changes | Medium | Deeper | Open | As reported
TC-Q6 | Test & CI/CD | auth-coverage matches by function name; floor of 50 vs 100 modules | Medium | Quick | Open | As reported
TC-CI3 | Test & CI/CD | Coverage is never measured in CI | Medium | Quick | Open | As reported
TC-CI5 | Test & CI/CD | Security scanning is 5 regex patterns over the working tree only; no SAST | Medium | Quick | Fixed | Verified in code | Patterns widened (DB/SMTP/conn-string/more prefixes); -e bug fixed; false positives tightened.
TC-CI10 | Test & CI/CD | No backend type-check, and lint warnings never fail | Medium | Deeper | Open | As reported
TC-D7 | Test & CI/CD | The deployed tree is mutable and the deploy is not pinned to an artifact | Medium | Deeper | Open | As reported
TC-D8 | Test & CI/CD | CI has no concurrency group; trigger SHA != deployed SHA | Medium | Quick | Open | As reported
TC-E2 | Test & CI/CD | Publicly known dev defaults, guarded only by NODE_ENV | Medium | Quick | Open | As reported
TC-E3 | Test & CI/CD | No rotation story for anything; ENCRYPTION_KEY effectively unrotatable | Medium-High | Process | Open | As reported
TC-E4 | Test & CI/CD | The secret scan is blind to git history; documented past exposure unverified | Medium | Quick to check | Fixed | Verified in code | scripts/scan-history-secrets.sh. RUN: the Groq key spans 177 commits from 51b57ae (2026-07-06) to HEAD. Purge declined; rotation done instead.
TC-R3 | Test & CI/CD | Deploys are not traceable to commits | Medium-High | Quick | Open | As reported
TC-R1 | Test & CI/CD | There are no releases, tags or changelog; version frozen at 0.1.0 | Medium | Quick | Open | As reported
TC-Q5 | Test & CI/CD | Registration-only tests read as behavioural coverage | Low-Medium | Classify | Open | As reported
TC-R4 | Test & CI/CD | Merge commits carry the least information; commit messages are the changelog | Low-Medium | Quick | Open | As reported
TC-CI4 | Test & CI/CD | npm audit reports but does not block, with no expiry | Low-Medium | Quick | Open | As reported
TC-F2 | Test & CI/CD | --runInBand costs 3x runtime for no observed benefit | Low | Quick | Open | As reported
TC-F3 | Test & CI/CD | Expected-error noise in the CI log trains people to ignore red output | Low | Quick | Open | As reported
TC-F1 | Test & CI/CD | No flakiness across 90 runs - measured, not assumed | Low | No action (positive finding) | Closed | As reported
TC-CI9 | Test & CI/CD | Pipeline speed is not a problem | Low | No action (positive finding) | Closed | As reported
UI-F1 | Desktop UI | The home screen is a static HTML mock inside an iframe (1,440 lines of raw assets) | Critical | Structural | Open | As reported
UI-F2 | Desktop UI | There is no desktop breakpoint - the entire app lays out at 640px | Critical | Structural | Open | Verified in code | sm: 216 and lg: 30 unchanged since the audit; xl: has moved 0 -> 3 and 2xl: 0 -> 1, so the work has barely started
UI-F4 | Desktop UI | 565 form fields render a label with no association to their control | Critical | Mechanical | Partially fixed | Verified in code | aria-invalid 0 -> 12 and aria-describedby 0 -> 19 since the audit
UI-F5 | Desktop UI | The documented way to build a screen does not exist | Critical | Docs + code | Open | As reported
UI-A2 | Desktop UI | features/sales/ui.tsx is a shadow design system imported by 10 feature areas | Critical | Structural | Open | As reported
UI-F3 | Desktop UI | Every page self-caps at 1152px (mx-auto max-w-6xl at 86 call sites) | High | Mechanical | Largely fixed | Verified in code | max-w-6xl down from 86 to 2; replaced by semantic max-w-standard / max-w-wide / max-w-reading tokens
UI-F6 | Desktop UI | Duplication: the same UI reimplemented instead of shared | High | Mechanical | Open | As reported
UI-F7 | Desktop UI | Component architecture: god files and no page-level decomposition | High | Structural | Open | As reported
UI-F13 | Desktop UI | Accessibility: .micro at 3.01:1 contrast, menu keyboard nav, heading structure | High | Mechanical | Open | As reported
UI-F16 | Desktop UI | Tech stack gaps: no frontend tests, no a11y lint | High | Tooling | Open | As reported
UI-A3 | Desktop UI | Local re-implementations found only by reading (Segmented x4, Panel x6, FormButtons x7) | High | Mechanical | Open | As reported
UI-A4 | Desktop UI | Raw JSON shown to end users | High | Code | Open | As reported
UI-F8 | Desktop UI | Data fetching: no cache, duplicate requests, client-side filtering over a truncated 50-row window | Medium | Code | Partially fixed | Verified in code | Reclassified by the audit as a correctness defect, not performance. Finance hub fixed server-side in commit 9c5337d; other hubs outstanding
UI-F9 | Desktop UI | Responsive failures beyond the breakpoint gap | Medium | Mechanical | Open | As reported
UI-F10 | Desktop UI | Loading states: five different idioms, inconsistently applied | Medium | Mechanical | Open | As reported
UI-F11 | Desktop UI | Empty states: good primitive, uneven coverage, generic copy | Medium | Mechanical | Open | As reported
UI-F12 | Desktop UI | Errors and edge cases, including a live errMsg double-wrap defect | Medium | Code | Open | As reported
UI-F14 | Desktop UI | Visual and UX consistency: 122 raw Tailwind palette colours bypassing the tokens | Medium | Mechanical | Open | As reported
UI-F15 | Desktop UI | Developer experience | Medium | Tooling | Open | As reported
UI-F17 | Desktop UI | The visual language is a well-executed template and reads as one - typography and density | Medium | Token pass | Open | As reported
NEW-01 | Test & CI/CD | Dockerfile deps stage never copied packages/, so `@praxis/shared` (a file: dependency) could not be linked — the image had no invoicing module and every final_invoice route 404'd | Critical | Docker | Fixed | Verified in code | Layer was cached from before the dep existed, so builds kept passing. Also a time bomb: the next package.json change would fail the build outright. Found by running the test suite. Commit 5ed5870.
NEW-02 | Test & CI/CD | scripts/deploy.sh git-pulls the repo containing itself, so bash keeps executing the OLD file — every change to it took effect one deploy late | Critical | Shell | Fixed | Verified in code | Pre-existing. Surfaced when a fix to the backup step was pulled and the run failed with the exact bug it fixed. Now pulls then re-execs. Reproduced standalone. Commit cdc034d.
NEW-03 | Test & CI/CD | Working tree is CRLF while every git blob is LF; a shell script edited on Windows becomes unparseable on the Linux server | Critical | Config | Fixed | Verified in code | rollback.sh failed with `syntax error near unexpected token $'do\r'` — the recovery script could not run at all. .gitattributes added; CI now asserts every tracked *.sh is LF and passes bash -n. Commit 54e3f2c.
NEW-04 | Data Integrity | config/database.js is dead code in the API process — initDatabase() is defined and never called anywhere in src/ | High | Code | Open | Verified in code | Its pool is permanently null, so query() always throws 'db pool not initialised'. Found because the first readiness probe used it and reported Postgres down on a healthy server. Consistent with DATA 4.1 (the RLS layer does not exist). Needs its own pass.
NEW-05 | Data Integrity | Depreciation rows already written with posted=true and entry_id NULL — the register reports accumulated depreciation the trial balance does not contain | Critical | Data repair | Open | Verified in code | Damage left by DI-5.5. Net book value understated; any asset disposed in the window computed gain/loss from the phantom figure. scripts/db/reconcile-depreciation.js finds and optionally clears the false flags (commit 1de3ab6). NOT YET RUN.
NEW-06 | Observability | pino-pretty transport was spawned under NODE_ENV=test, leaking a worker thread per Jest process | Low | Config | Fixed | Verified in code | Caused 'A worker process has failed to exit gracefully'. Bought nothing — jest.setup.js already silences output. Pretty-printing is now development-only. Commit 5ed5870.

## Summary
Praxis LS - consolidated audit register, 2026-08-04
Seven Phase-0 audits. One row per headline finding on the Register sheet.
Audit | Critical | High | Medium-High | Medium | Low-Medium | Low | Total
Security | 3 | 6 | 0 | 9 | 0 | 6 | 24
Data Integrity | 6 | 16 | 0 | 10 | 0 | 1 | 33
Observability | 13 | 12 | 0 | 6 | 0 | 0 | 31
API Contract | 5 | 8 | 0 | 13 | 0 | 4 | 30
Perf & Architecture | 3 | 9 | 0 | 6 | 0 | 2 | 20
Test & CI/CD | 7 | 19 | 2 | 12 | 3 | 4 | 47
Desktop UI | 5 | 7 | 0 | 8 | 0 | 0 | 20
Total | 42 | 77 | 2 | 64 | 3 | 17 | 205
Status roll-up
Open | 164
Partially fixed | 5
Fixed | 31
Largely fixed (superseded) | 0
Closed | 3
Independently verified in code | 40